## Blank
SIMPLE GANTT CHART TEMPLATE
PROJECT TITLE
PROJECT MANAGER
COMPANY NAME
DATE
[7 empty] | PHASE ONE | [14 empty] | PHASE TWO | [14 empty] | PHASE THREE | [14 empty] | PHASE FOUR
TASK | TASK | TASK | START | DUE | DURATION | PCT OF TASK | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 5 |  |  |  |  | WEEK 6 |  |  |  |  | WEEK 7 |  |  |  |  | WEEK 8 |  |  |  |  | WEEK 9 |  |  |  |  | WEEK 10 |  |  |  |  | WEEK 11 |  |  |  |  | WEEK 12
ID | TITLE | OWNER | DATE | DATE | IN DAYS | COMPLETE | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F
1 | Project Conception and Initiation
1.1 | Project Charter |  |  |  |  | 100%
1.1.1 | Project Charter Revisions |  |  |  |  | 0%
1.2 | Research |  |  |  |  | 0%
1.3 | Projections |  |  |  |  | 0%
1.4 | Stakeholders |  |  |  |  | 0%
1.5 | Guidelines |  |  |  |  | 0%
1.6 | Project Initiation |  |  |  |  | 0%
2 | Project Definition and Planning
2.1 | Scope & Goal Setting |  |  |  |  | 0%
2.2 | Budget |  |  |  |  | 0%
2.3 | Communication Plan |  |  |  |  | 0%
2.4 | Risk Management |  |  |  |  | 0%
3 | Project Launch and Execution
3.1 | Status & Tracking |  |  |  |  | 0%
3.2 | KPIs |  |  |  |  | 0%
3.2.1 | Monitoring |  |  |  |  | 0%
3.2.2 | Forecasts |  |  |  |  | 0%
3.3 | Project Updates |  |  |  |  | 0%
3.3.1 | Chart Updates |  |  |  |  | 0%
4 | Project Performance / Monitoring
4.1 | Project Objectives |  |  |  |  | 0%
4.2 | Quality Deliverables |  |  |  |  | 0%
4.3 | Effort and Cost Tracking |  |  |  |  | 0%
4.4 | Project Performance |  |  |  |  | 0%

## Example
SIMPLE GANTT CHART TEMPLATE
PROJECT TITLE | Greencodify
PROJECT MANAGER | Sara
COMPANY NAME | Greencodify
DATE | 18.03.2025*
[7 empty] | PHASE ONE | [14 empty] | PHASE TWO | [14 empty] | PHASE THREE | [14 empty] | PHASE FOUR
TASK | TASK | TASK | START | DUE | DURATION | PCT OF TASK | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 5 |  |  |  |  | WEEK 6 |  |  |  |  | WEEK 7 |  |  |  |  | WEEK 8 |  |  |  |  | WEEK 9 |  |  |  |  | WEEK 10 |  |  |  |  | WEEK 11 |  |  |  |  | WEEK 12
ID | TITLE | OWNER | DATE | DATE | IN DAYS | COMPLETE | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F
1 | Project Conception and Initiation
1.1 | Project Charter | Nikolai | 2023-03-12 | 2023-03-15 | 3 | 100%
1.1.1 | Project Charter Revisions | Nikolai | 2023-03-15 | 2023-03-16 | 1 | 100%
1.2 | Research | Sara | 2023-03-15 | 2023-03-21 | 6 | 90%
1.3 | Projections | Sara | 2023-03-16 | 2023-03-22 | 6 | 40%
1.4 | Stakeholders | Fredrik | 2023-03-17 | 2023-03-22 | 5 | 70%
1.5 | Guidelines | Sara | 2023-03-18 | 2023-03-22 | 4 | 60%
1.6 | Project Initiation | Nikolai | 2023-03-23 | 2023-03-23 |  | 50%
2 | Project Definition and Planning
2.1 | Scope and Goal Setting | Fredrik | 2023-03-24 | 2023-03-28 | 4 | 5%
2.2 | Budget | Fredrik | 2023-03-29 | 2023-04-02 | 4 | 30%
2.3 | Communication Plan | Sara |  |  |  | 0%
2.4 | Risk Management | Nikolai |  |  |  | 0%
3 | Project Launch and Execution
3.1 | Status and Tracking | Fredrik |  |  |  | 0%
3.2 | KPIs | Fredrik |  |  |  | 0%
3.2.1 | Monitoring | Sara |  |  |  | 0%
3.2.2 | Forecasts | Sara |  |  |  | 0%
3.3 | Project Updates | Sara |  |  |  | 0%
3.3.1 | Chart Updates | Nikolai |  |  |  | 0%
4 | Project Performance / Monitoring
4.1 | Project Objectives | Nikolai |  |  |  | 0%
4.2 | Quality Deliverables | Nikolai |  |  |  | 0%
4.3 | Effort and Cost Tracking | Fredrik |  |  |  | 0%
4.4 | Project Performance | Fredrik |  |  |  | 0%